## Slide 1: GDP Group 18
Unmanned Aircraft Camera Module
Notes: Michael Start
Welcome

## Slide 2: The Next 20 Minutes
Problem
Specification
Breakdown of sanity tasks
Project management
Progress
Next Steps
Notes: Michael
Describe our project: problem, specification, etc
How we’ve managed the project so far
Progress
Future plans

## Slide 3: Problem
Notes: Michael

## Slide 4: Problem
Currently, an autopiloted UAV may take pictures while it is in the air
On many UAV systems the aircraft must land before images can be downloaded and viewed
These images could be inadequate
Wireless transmission of images preferred
Notes: Michael

## Slide 5: SkyCircuits Autopilot (SC2)
http://www.skycircuits.com/
Notes: Michael

## Slide 6: Specification & Progress Overview
Notes: John

## Slide 7: Specification
Notes: John“To design, build and test an electronic module capable of capturing still images from an unmanned aerial vehicle (UAV) and transmitting the images to a base station. The module must use the UAV autopilot’s low-bandwidth RS485 serial link (38.4 kBaud). A program must be written to interface with the base station software over a TCP/IP link, allowing image data to be received and displayed to the user. The electronic module will be constructed using strip-boards and will later be implemented on PCB if time is available.

## Slide 8: Spec: High Priority
Prompt (from base station) to capture and download image
Image encoding
Minimise download time (less than 3 minutes)
Notes: John

## Slide 9: Spec: High Priority
Prompt (from base station) to capture and download image
  GUI under construction
Progressive Image encoding/decoding
Minimise download time (less than 3 minutes)
  Approximately 10 seconds
Notes: John

## Slide 10: Spec: Medium Priority
Module weight < 250g
Image resolution: 640 x 480
Cancel image download whilst downloading
Notes: John

## Slide 11: Spec: Medium Priority
Module weight < 250g
  ##PUT IN MEASUREMENT##
Image resolution: 640 x 480
  ##MULTIPLE?##
Cancel image download whilst downloading
Notes: John

## Slide 12: Spec: Low Priority
Resend an image if corrupted
Interrupt download of image, save incomplete image
Select resolution of image
Display progress indicator of download
(User defined) Automatic image capture
Colour images (select between colour / BW)
Notes: John

## Slide 13: Spec: Low Priority
Resend an image if corrupted
Interrupt download of image, save incomplete image
Select resolution of image
Display progress indicator of download
(User defined) Automatic image capture
Colour images (select between colour / BW)
Notes: John

## Slide 14: Spec: Deliverables
Hardware: Constructed camera module (on PCB if possible)
Software: Firmware for module, Software for base station
Documentation: Technical and User Documentation
Public Repository: Open source, publically accessible repository, includes all the above.
Notes: John

## Slide 15: Spec: Deliverables
Hardware: Constructed camera module (on PCB if possible)
Software: Firmware for module, Software for base station
Documentation: Technical and User Documentation
Public Repository: Open source, publically accessible repository, includes all the above.
  https://github.com/andybusse/uavcamera
Notes: John

## Slide 16: Project Management
Notes: Mitch:
Manage the human resources available and how best to utilise them.
Pre-emptive steps to take care of problems that might arise: always know what we’re doing
Manage time resource and measure the progress of the project, so we can adapt quickly if behind.

## Slide 17: Recap – Last Seminar
Skills Audit
Risk management
Project plan, breakdown and progress

## Slide 18: Project Management: Contingencies + Risk Management
Risk | Likelihood (1: Low, 5: High) | Impact (1: Low, 5: High) | Action
Faulty Components | 4 | 4 | Order spares where feasible. Source new/replace faulty components at high speed otherwise.
Team member becoming unavailable | 2 | 4 | At least two people on each task. Reallocating people to different tasks as required
Team member facing difficulties | 5 | 2 | At least two people per task. Good team communication. Prioritise necessary tasks first.
Notes: Mitch
Why? Problems will arise. Need an appropriate plan for any problem that may occur as to not waste any time resource.
FC:
  L4: experience with providers, general short circuits, loss, etc. (many factors)
  I4: Project hardware dependent. Very real and serious problem.
  Very time consuming problem (delivery, many other parts depend on this).
Team:
  L2: Southampton is a safe place. Members take care of themselves.
  I4: Each person is 20% of primary resource (needed to get things done)
  All tasks can be done by different people, so catching up is easy.
Difficulties:
  L5: Very challenging project ranging from hardware to software difficulties.
  I2: Expected. Does not directly slow down progress.
  Teamwork is more efficient than lone work

## Slide 19: Obstacles
Faulty Components
  Camera was faulty
  Bug in Autopilot code
  Risk Assessment Action: Order spares where feasible. Source new/replace faulty components at high speed otherwise.
  Actual Action:
    Camera - Ordered new (expensive) camera, modified project plan to fit around delay.
    Autopilot – Extensive debugging alongside supplier of autopilot

## Slide 20: Project Management: Contingencies + Risk Management
Risk | Likelihood (1: Low, 5: High) | Impact (1: Low, 5: High) | Action
Faulty Components | 4 | 4 | Order spares where feasible. Source new/replace faulty components at high speed otherwise.
Team member becoming unavailable | 2 | 4 | At least two people on each task. Reallocating people to different tasks as required
Team member facing difficulties | 5 | 2 | At least two people per task. Good team communication. Prioritise necessary tasks first.
Notes: Mitch
Why? Problems will arise. Need an appropriate plan for any problem that may occur as to not waste any time resource.
FC:
  L4: experience with providers, general short circuits, loss, etc. (many factors)
  I4: Project hardware dependent. Very real and serious problem.
  Very time consuming problem (delivery, many other parts depend on this).
Team:
  L2: Southampton is a safe place. Members take care of themselves.
  I4: Each person is 20% of primary resource (needed to get things done)
  All tasks can be done by different people, so catching up is easy.
Difficulties:
  L5: Very challenging project ranging from hardware to software difficulties.
  I2: Expected. Does not directly slow down progress.
  Teamwork is more efficient than lone work

## Slide 21: Project Management: Contingencies + Risk Management
Risk | Likelihood (1: Low, 5: High) | Impact (1: Low, 5: High) | Action
Task overrunning | 4 | 3 | Plenty of redundancy planned into Gantt Chart. Reallocation of resources when necessary. Good team communication.
Loss of files/source code | 1 | 5 | Proper use of source control. Back ups.
Loss of access to facilities | 1 | 4 | Work from home laboratory. Buy missing components if necessary.
Acts of a wrathful God | 1/∞ | ∞ | Pray. Cry. Adapt.
Notes: Mitch
Risk
  L4: Impossible to always know what other is doing without consistent, non-stop (unrealistic) communication.
  I3: Results in wasted time and man resource, slowing project down until progress is reassessed.
  Action: Reassess regularly
Loss
  L1: Many countermeasures available. Very rare occurrence.
  I5: Project relies a lot on software (git/svn).

## Slide 22: Project Management: Contingencies + Risk Management
Risk | Likelihood (1: Low, 5: High) | Impact (1: Low, 5: High) | Action
Task overrunning | 4 | 3 | Plenty of redundancy planned into Gantt Chart. Reallocation of resources when necessary. Good team communication.
Loss of files/source code | 1 | 5 | Proper use of source control. Back ups.
Loss of access to facilities | 1 | 4 | Work from home laboratory. Buy missing components if necessary.
Acts of a wrathful God | 1/∞ | ∞ | Pray. Cry. Adapt.
Notes: Mitch
Risk
  L4: Impossible to always know what other is doing without consistent, non-stop (unrealistic) communication.
  I3: Results in wasted time and man resource, slowing project down until progress is reassessed.
  Action: Reassess regularly
Loss
  L1: Many countermeasures available. Very rare occurrence.
  I5: Project relies a lot on software (git/svn).

## Slide 23: Project Management: Contingencies + Risk Management
Risk | Likelihood (1: Low, 5: High) | Impact (1: Low, 5: High) | Action
Task overrunning | 4 | 3 | Plenty of redundancy planned into Gantt Chart. Reallocation of resources when necessary. Good team communication.
Loss of files/source code | 1 | 5 | Proper use of source control. Back ups.
Loss of access to facilities | 1 | 4 | Work from home laboratory. Buy missing components if necessary.
Acts of a wrathful God | 1/∞ | ∞ | Pray. Cry. Adapt.
Notes: Mitch
Risk
  L4: Impossible to always know what other is doing without consistent, non-stop (unrealistic) communication.
  I3: Results in wasted time and man resource, slowing project down until progress is reassessed.
  Action: Reassess regularly
Loss
  L1: Many countermeasures available. Very rare occurrence.
  I5: Project relies a lot on software (git/svn).

## Slide 24: Breakdown of Progress
Notes: Andy

## Slide 25: System Block Diagram
Notes: andy

## Slide 26: Breakdown of Progress: UAV Payload
Camera Module Communication
Image Encoding/Transmission
  Basic Raw Encoding (JPEG)
  Custom (compressed) encoding
Payload Module Construction
Notes: andy

## Slide 27: Breakdown of Progress: UAV Payload
Camera Module Communication
Image Encoding/Transmission
  Basic Raw Encoding (JPEG)
  Custom (compressed) encoding
Payload Module Construction
Notes: andy

## Slide 28: Camera Communication
Serial at ###### baud
Commands including RESET, BLAH
Image resolutions:
  Blah
Testing?

## Slide 29: Image Encoding/Transmission
Autopilot ensures error free transmission
  But does not ensure reliable transmission
Used packet structure
  Each packet numbered
  Variable size
GS can detect missing packets and ask for resend
Testing?
Autopilot problems

## Slide 30: Payload Module Construction
Breadboard and Stripboard prototypes
PCB design:
  <insert image here>
Electrical testing?

## Slide 31: Breakdown of Tasks: Base Station
TCP/IP Base Station Communications
Decode Image (JPEG)
Custom decoding
User Interface
Notes: Andy

## Slide 32: Breakdown of Tasks: Base Station
TCP/IP Base Station Communications
Decode Image (JPEG)
Custom decoding
User Interface
Notes: Andy

## Slide 33: Ground Station <-> Payload Communication
Autopilot -> Payload comms: Message sending
Autopilot
Payload
Message
Ground Station

## Slide 34: Ground Station <-> Payload Communication
Payload -> Autopilot comms: Shared memory
Autopilot
Payload
Shared memory
Ground Station

## Slide 35: TCP/IP Basestation Comms
SkyCircuits ground control software exposes two ports: Data stream and Console
Ground Station
Data Port
Console Port

## Slide 36: Ground Station <-> Payload Communication
Autopilot -> Payload comms: Message sending
Autopilot
Payload
Message
Ground Station

## Slide 37: Ground Station <-> Payload Communication
Autopilot -> Payload comms: Message sending
Autopilot
Payload
Message
Ground Station
Console Port
Our GUI

## Slide 38: Ground Station <-> Payload Communication
Payload -> Autopilot comms: Shared memory
Autopilot
Payload
Shared memory
Ground Station

## Slide 39: Ground Station <-> Payload Communication
Payload -> Autopilot comms: Shared memory
Autopilot
Payload
Shared memory
Ground Station
Data Port
Our GUI

## Slide 40: Breakdown of Tasks: Complete System
Background Research
UAV module / Base station Integration
Whole System Testing
Delicious Report Writing (WIP)
Notes: Andy

## Slide 41
Properly modify Gantt chart

## Slide 42: Demo

## Slide 43: Extensions
Multiple cameras at once
Multiple types of camera
Video
SD filesystem access

## Slide 44: Questions?
We NYANED for 1200.0 seconds!